## Backlog
| User Story | Tasks | Status | Week Completed
0 | Pre-production
|  | Market research | Done | Week 4
|  | Create a consumer profile | Done | Week 4
Create a risk assessment for the project
Paper prototype
1 | As a player I want to be able to sort objects
|  | Create concept art for the layout of the sorting screen |  |  | 1 - Necessary for creation of MVP (High priority; marked as Critical on JIRA)
Implement a system in Unity that allows players to drag an item to a category
Implement a system in Unity that allows an object from a list to appear in the middle of the screen ready for sorting
|  | Implement a system in Unity that checks whether the object has been sorted correctly or incorrectly |  |  | 2 - Needed but not required for the MVP (Mid priority; marked as Major on JIRA)
Research casual mechanic of sorting/matching
|  | Come up with the two initial sorting categories |  |  | 3 - "Nice to have" if time allows (Low priority; marked as Minor on JIRA)
Come up with a list of objects (5 for MVP) that can be sorted for each category
1 | As a player I want to be able to earn rewards
Research reward schedules
Design a schedule for the rewards that the players can receive
Design the rewards that a player will be able to obtain
1 | As a player I want to be able to decorate my planet
Research how to create 'awe' and 'wonder'
Design assets; fireflies
1 | As a player I want to be able to grow different plants
Implement a system in Unity that allows plants to grow in real time
1 | As a player I want to be able to zoom into different parts of my planet
1 | As a player I want to be able to rotate around my planet
Implement a system in Unity that allows players to drag left or right to rotate their planet
1 | As a player I want to be able to spend and earn "energy"
2 | As a player I want to be able to progress to unlock new sorting categories and their corresponding items
2 | As a player I want a menu system so that I can navigate the game
Main menu background art
Settings/options button
Implement menu system in Unity
2 | As a player I want to be able to fill out my collection journal
2 | As a player I want to have a summary of my planet in my journal so that I can compare with my friends
Create a 'stats' page in collection log
Pull data from Unity and have it display as figures for player to see in collection log
2 | As a player I want to see a consistent art style
Universal button style
Art style guide
2 | As a player I want to be able to name my planet and have it visible on the game screen
2 | As a player I want to be able to play the game on different devices regardless of resolution
2 | As a player I want to be able to playtest the game
Create an MVP (minimum viable product)
Create a feedback form that allows players to report bugs
2 | As a player I want to have an elegant UI system
Research mobile game UI; focus primarily on similar games in the market
3 | As a player I want the game to be animated
Animation frames - trees
3 | As a player I want the game to have audio feedback
SFX - button press, new reward unlocked
OST - Day time
OST - Night time
Implement SFX into Unity
Implement OST into Unity
3 | As a player I want the final product to be clean and polished
3 | As a player I want to be able to change the season and have it affect my deocrations
Create a mood board for Spring
Create a mood board for Summer
Create a mood board for Autumn
Create a mood board for Winter
Create a colour palette for Spring
Create a colour palette for Summer
Create a colour palette for Autumn
Create a colour palette for Winter
3
3

## Risk Assessment
Risk | Impact Level | Likelihood
Poor productivity | High | Medium |  | High
Software bugs | High | Medium |  | Medium
Use of new technology | High | Medium |  | Low
Not creating an MVP within a reasonable amount of time | High | Medium
A loss of work | Medium | Medium
The game may not be what target audience wants | Medium | Medium | Proposed course of action for each risk can be found in detailed Risk Assessment documentation located in Management folder on Github repo
Risk of not including the key features | Medium | Medium
Feature creeping | Medium | Medium
Discovering new requirements | Medium | Medium
Misestimation of project schedule | Medium | Medium
Time away due to unforseen circumstances | Medium | Medium
Lack of communication between group members | Medium | Low
Clash of schedules between group members | Low | High