## Backlog
| User Story | Tasks | Status | Week Completed
0 | Pre-production
|  | Market research | Done | Week 4
|  | Create a consumer profile | Done | Week 4
Create a risk assessment for the project
1 | As a player I want to be able to sort objects
|  | Create concept art for sorting screen |  |  | 1 - Necessary for creation of MVP (High priority)
|  | Research casual mechanic of sorting/matching |  |  | 2 - Needed but not a part of the core game (Mid priority)
3 - "Nice to have" if time allows (Low priority)
1 | As a player I want to be able to earn rewards
Research reward schedules
Design a schedule for the rewards that the players can receive
Design the rewards that a player will be able to obtain
1 | As a player I want to be able to decorate my planet
Research how to create 'awe' and 'wonder'
1 | As a player I want to be able to grow different plants
Implement a system in Unity that allows plants to grow in real time
1 | As a player I want to be able to zoom into different parts of my planet
1 | As a player I want to be able to rotate around my planet
Implement a system in Unity that allows players to drag left or right to rotate their planet
1 | As a player I want to be able to change the season and have it affect my deocrations
Create a mood board for Spring
Create a mood board for Summer
Create a mood board for Autumn
Create a mood board for Winter
Create a colour palette for Spring
Create a colour palette for Summer
Create a colour palette for Autumn
Create a colour palette for Winter
1 | As a player I want a menu system so that I can navigate the game
Main menu background art
Settings/options button
Implement menu system in Unity
1 | As a player I want to be able to fill out my collection log
1 | As a player I want to have a summary of my planet in my log so that I can compare with my friends
Create a 'stats' page in collection log
Pull data from Unity and have it display as figures for player to see in collection log
1 | As a player I want to see a consistent art style
Universal button style
Art style guide
2 | As a player I want to be able to name my planet and have it visible on the game screen
2 | As a player I want to be able to play the game on different devices regardless of resolution
2 | As a player I want to be able to playtest the game
Create an MVP (minimum viable product)
Create a feedback form that allows players to report bugs
2 | As a player I want to have an elegant UI system
Research mobile game UI; focus primarily on similar games in the market
3 | As a player I want the game to be animated
Animation frames - trees
3 | As a player I want the game to have audio feedback
SFX - button press, new reward unlocked
OST - Day time
OST - Night time
Implement SFX into Unity
Implement OST into Unity
3 | As a player I want the final product to be clean and polished
3
3