## Backlog
| User Story | Tasks | Status | Week Completed
0 | Pre-production
|  | Market research | Done | Sprint 2
|  | Create a consumer profile/psychographic | Done | Sprint 4
|  | Create a risk assessment for the project | Done | Sprint 2
|  | Paper prototype | Done | Sprint 4
Project timeline?
1 | As a player I want to be able to sort objects
|  | Create concept art for the layout of the sorting screen |  |  | 1 - Necessary for creation of MVP (High priority; marked as Critical on JIRA)
|  | Implement a system in Unity that allows players to drag an item to a category |  |  | 2 - Needed but not required for the MVP (Mid priority; marked as Major on JIRA)
|  | Implement a system in Unity that allows an object from a list to appear in the middle of the screen ready for sorting |  |  | 3 - "Nice to have" if time allows (Low priority; marked as Minor on JIRA)
Implement a system in Unity that checks whether the object has been sorted correctly or incorrectly
Research casual mechanic of sorting/matching
Come up with the two initial sorting categories
Come up with a list of objects (5 for MVP) that can be sorted for each category
|  | Create an animation that will show players how to drag objects to sort them into categories | Done
1 | As a player I want to be able to earn rewards
Research reward schedules
Design a schedule for the rewards that the players can receive
Design the rewards that a player will be able to obtain (seeds)
1 | As a player I want to be able to decorate my planet
|  | Research how to create 'awe' and 'wonder' | Done | Sprint 4
Design flowers/trees/bushes that correspond with the seeds the player can unlock
1 | As a player I want to be able to grow different plants
|  | Implement a system in Unity that allows plants to grow in real time | Done | Sprint 2
Implement a "growth tick" that requires the player to water their plant every 6 hours in order to progress it's growth
1 | As a player I want to be able to zoom into different parts of my planet
|  | Implement a system in Unity that allows player to use a pinching gesture to zoom in to their planet | Done | Sprint 3 (not set as task)
|  | Create an pinching hand animation that will be used to show players how to zoom in | Done
1 | As a player I want to be able to rotate around my planet
|  | Implement a system in Unity that allows players to drag left or right to rotate their planet | Done | Sprint 2
1 | As a player I want to be able to spend and earn "energy"
Implement a system in Unity that subtracts an energy point every time an object is sorted (successful or unsuccessful)
Implement a system in Unity that allows the player to collect "stars" from fully grown objects
Create a rarity table that dictates how much energy/stars can be earned for each type of object
2 | As a player I want to be able to progress to unlock new sorting categories and their corresponding items
2 | As a player I want a menu system so that I can navigate the game
Main menu background art
|  | Menu flow diagram | Done | Sprint 3
Settings/options button
Implement menu system in Unity
2 | As a player I want to be able to fill out my collection journal
2 | As a player I want to have a summary of my planet in my journal so that I can compare with my friends
Create a 'stats' page in collection log
Pull data from Unity and have it display as figures for player to see in collection log
2 | As a player I want to see a consistent art style
Universal button style
Art style guide
2 | As a player I want to be able to name my planet and have it visible on the game screen
|  | Implement the ability to take in player input for the purpose of naming their planet | Done | Sprint 3
|  | Implement a system that saves the player's planet name across game sessions | Done | Sprint 3
2 | As a player I want to be able to play the game on different devices regardless of resolution
Implement a system in Unity that deals with UI scaling
2 | As a player I want to be able to playtest the game
Create an MVP (minimum viable product)
Create a feedback form that allows players to report bugs
2 | As a player I want to have an elegant UI system
Research mobile game UI; focus primarily on similar games in the market
3 | As a player I want the game to be animated
Animation frames - trees
3 | As a player I want the game to have audio feedback
SFX - button press, new reward unlocked
OST - Day time
OST - Night time
Implement SFX into Unity
Implement OST into Unity
3 | As a player I want the final product to be clean and polished
3 | As a player I want to be able to change the season and have it affect my deocrations
|  | Create a mood board for Spring | Done | Sprint 2
|  | Create a mood board for Summer | Done | Sprint 2
|  | Create a mood board for Autumn | Done | Sprint 2
|  | Create a mood board for Winter | Done | Sprint 2
|  | Create a colour palette for Spring | Done | Sprint 2
|  | Create a colour palette for Summer | Done | Sprint 2
|  | Create a colour palette for Autumn | Done | Sprint 2
|  | Create a colour palette for Winter | Done | Sprint 2
3
3

## Risk Assessment
Risk | Impact Level | Likelihood
Poor productivity | High | Medium |  | High
Software bugs | High | Medium |  | Medium
Use of new technology | High | Medium |  | Low
Not creating an MVP within a reasonable amount of time | High | High
A loss of work | Medium | Medium
The game may not be what target audience wants | Medium | Medium | Proposed course of action for each risk can be found in detailed Risk Assessment documentation located in Management folder on Github repo
Risk of not including the key features | Medium | Medium
Feature creeping | Medium | Medium
Discovering new requirements | Medium | Medium
Misestimation of project schedule | Medium | High
Time away due to unforseen circumstances | Medium | Medium
Lack of communication between group members | Medium | Medium
Clash of schedules between group members | Low | High
Misestimation of individual tasks | Medium | High