## Project Backlog
| User Story | Tasks | Status | Week Completed
0 | Pre-production
As a player I want to be introduced to the game by Praesul
Come up with a piece of dialogue that Praesul says in order to greet the player and provide them with their goal
Concept art for Praesul
Final artwork for Praesul
Using placeholder assets, implement Praesul’s greeting into Unity project
|  | Implement Praesul’s artwork into Unity |  |  | 1 - Necessary for creation of MVP (High priority; marked as Critical on JIRA)
| As a player I want to be given a choice of two seeds at the start of the tutorial |  |  |  | 2 - Needed but not required for the MVP (Mid priority; marked as Major on JIRA)
|  | Design the first interesting starter seed for the player to choose from |  |  | 3 - "Nice to have" if time allows (Low priority; marked as Minor on JIRA)
Design the second interesting starter seed for the player to choose from
Come up with a piece of dialogue that Praesul will say to the player when providing them with a choice of seeds
In Unity, implement the ability for the player to choose between the two starter seeds
|  | In Unity, implement the dialogue where Praesul tells the player about the seeds before offering them a choice |  |  | Done
| As a player I do not want to know what the seeds will grow into until I grow them myself |  |  |  | In Progress
| As a player I want acquired seeds to be stored in the backpack |  |  |  | Broken
| As a player I want seeds to hint as to what they will become with their artwork alone |  |  |  | Not Started
As a player I want seeds to have an interesting design that makes me curious
As a player I want the trees/plants to evoke awe and wonder (where possible)
As a player I want seeds to be able to change to ‘saplings’ once tapped/dibbed
As a player I want to be alerted within the backpack screen when a sapling requires watering
As a player I want saplings to start growing in the backpack once I have watered them
As a player I want the game to progress/plants to grow when I’m not physically watching or playing the game
As a player I want trees to mature; from the sapling stage to the mature stage
As a player I want to be alerted by the inventory icon when a plant is mature enough to be planted in the garden
As a player I want my trees to mature at a fair rate to a designed growth schedule
As a player I want to be given a set amount of plots(to begin with)
As a player I want to be able to ‘weed’ a plot of land with a tapping motion
As a player I want to be able to see weeded plots eventually grow weeds again if no plants are planted in that plot
As a player I want to be able to ‘plant’ my matured tree onto a plot of land that has been weeded
As a player I want to be able to harvest produce from fully grown mature plants/trees
As a player I want to be able to harvest both single yield objects(carrots) and multiple yield objects (apple tree)
As a player I want each tap to give me one of the total amount of produce (For example, 1 Tap = 1/6 produce)
As a player I want single yield objects to vanish once harvested
As a player I want multiple yield objects to remain after harvesting but then starts to grow yield again after a predetermined time
As a player I want to be able to be alerted by the basket icon that there are objects to be harvested somewhere within the plots
As a player I want to be able to tap the basket alert icon, which then takes me to the garden screen
As a player I want to be able to see my currency at all times (pebbles)
As a player I want to convert harvested produce into pebbles instantly
As a player I want to be shown my currency increase as I harvest my produce
As a player I would like the seed packet to alert me when a new seed is unlocked/can be purchased
As a player I want to be able to access the shop and purchase seeds
As a player I want to be able to see my currency reduce after a purchase
As a player I want to be able to see seeds I can and cannot purchase
As a player I want to be able to know what seeds grow into if I’ve already grown them before
As a player I want to be able to earn a larger amount of garden space(more plots) as I progress/buy space in the shop
As a player I want to be given tasks by Praesul at random intervals
As a player I want to only be able to have 1 task from Praesul at the same time
As a player I want to be rewarded by Praesul with monetary rewards and or with seeds which are new and that I’ve never grown before

## (DEPRECATED) Old Backlog
| User Story | Tasks | Status | Week Completed
0 | Pre-production
|  | Initial ideas and prototyping | Done | Sprint 1
|  | Game design document | Done | Sprint 2
|  | Market research | Done | Sprint 2
|  | Create a consumer profile/psychographic | Done | Sprint 4
|  | Create a risk assessment for the project | Done | Sprint 2
|  | Paper prototype | Done | Sprint 4
Project timeline
|  | Research how to keep players engaged | Done | Sprint 2
1 | As a player I want to be able to sort objects
|  | Create concept art for the layout of the sorting screen | Done | Sprint 5 | 1 - Necessary for creation of MVP (High priority; marked as Critical on JIRA)
|  | Implement a system in Unity that allows players to drag an item to a category | Done | Sprint 5 | 2 - Needed but not required for the MVP (Mid priority; marked as Major on JIRA)
|  | Implement a system in Unity that allows an object from a list to appear in the middle of the screen ready for sorting | Done | Sprint 5 | 3 - "Nice to have" if time allows (Low priority; marked as Minor on JIRA)
|  | Implement a system in Unity that checks whether the object has been sorted correctly or incorrectly | Done | Sprint 6
|  | Research casual mechanic of sorting/matching | Done | Sprint 5
|  | Come up with the two initial sorting categories | Done | Sprint 5
|  | Come up with a list of objects (5 for MVP) that can be sorted for each category | Done | Sprint 5 | Done
|  | Create an animation that will show players how to drag objects to sort them into categories | Done | Sprint 3 | In Progress
1 | As a player I want to be able to earn rewards |  |  |  | Broken
|  | Research reward schedules | Done | Sprint 4 | Not Started
|  | Design a schedule for the rewards that the players can receive | Done | Sprint 6
|  | Create a pop-up for when a player earns any type of seed so that they are aware they have things to plant | Done
|  | Create a pop-up for when a player earns a new reward that they haven't obtained before | Done
Design the rewards that a player will be able to obtain (seeds)
Implement scriptable objects in Unity so that the designer is able to add new player rewards and tweak variables as needed
Adapt the exisiting rewards system in Unity so that it makes use of the scriptable objects
Following the reward schedule created by the designer, use probabilities to decide how often a reward is given to the player
1 | As a player I want to be able to decorate my planet
|  | Research how to create 'awe' and 'wonder' | Done | Sprint 4 | IMPORTANT TO REVISIT (Some of these items are marked as 'Done' on JIRA but not in-game)
|  | Implement an inventory system that will be used to display the seeds the player has | Done | Sprint 4 | Credits (Sprint 10 - the UI panel is there, but is empty)
|  | Create concept art for the seed bag | Done | Sprint 4 | Items which have previously been marked as 'Done', but there is no evidence of them in the game build
|  | Design flowers/trees/bushes that correspond with the seeds the player can unlock |  |  | Main Menu (Logged during Sprint 10 - part of basic menu)
|  | Allow the user to tap on a fully-grown object and click a move button to re-arrange items on their planet |  |  | Ability to name the planet (Logged during Sprint 10 - part of basic menu)
|  | Final artwork for seed bag using flat art style |  |  | Player is currently unable to rotate their planet
Have date, time and version number on each build so that it is easier to determine when they were created (Logged during Sprint 10, we are using Calendar Versioning to keep track of current game version)
1 | As a player I want to be able to grow different plants
|  | Implement a system in Unity that allows plants to grow in real time | Done | Sprint 2
|  | As a UI element in Unity, create a countdown timer that displays time until object is fully grown | Done | Sprint 6
|  | Format the growth timer to display in days, hours, minutes and seconds | Done | Sprint 7
Implement a "growth tick" that requires the player to water their plant every 6 hours in order to progress it's growth
1 | As a player I want to be able to zoom into different parts of my planet
|  | Implement a system in Unity that allows player to use a pinching gesture to zoom in to their planet | Done | Sprint 3 (not set as task)
|  | Create an pinching hand animation that will be used to show players how to zoom in | Done | Sprint 3
1 | As a player I want to be able to rotate around my planet
|  | Implement a system in Unity that allows players to drag left or right to rotate their planet | Done | Sprint 2
1 | As a player I want to be able to spend and earn "energy"
|  | Implement a system in Unity that subtracts an energy point every time an object is sorted (successful or unsuccessful) | Done | Sprint 5
|  | Implement a system in Unity that allows the player to collect "stars" from fully grown objects | Done | Sprint 5
|  | Create a spreadsheet, that details how much energy can be earned from different objects | Done | Sprint 6
Implement the ability for the players to earn energy points over time, so that there is still a chance to sort even if the player isn't growing anything new
Come up with a different name for the energy bar and energy itself
2 | As a player I want to be taught how to play the game
|  | Design a tutorial that will guide players through the basics of the game (Part of paper prototype) | Done | Sprint 4
|  | Create an animation that will show players how to drag objects to sort them into categories | Done | Sprint 2
|  | Create an animation that will show players how to interact with UI elements and objects on their planet | Done | Sprint 3
Implement the animations that will be used to guide players through the sorting system
2 | As a player I want to feel relaxed while playing the game
|  | Conduct research into how to create a feeling of relaxation among players | Done | Sprint 2
|  | Create artwork for the beach that will be featured at the centre of the player's planet | Done | Sprint 3
2 | As a player I want to feel a sense of progression in the game
Determine the length of play for the game
Determine how the sorting mechanic will change over time
|  | Create digital mock ups that display parts of the game cycle (for the purpose of presenting to stakeholders) | Done | Sprint 5
2 | As a player I want to be able to tend to my planet in different ways
|  | Come up with a list of activites/"nurturing elements" that are associated with tending to a garden | Done | Sprint 8
|  | Come up with a list of potential "tending mechanics" based on the list of acitivites that you found as part of your research | Done | Sprint 8
2 | As a player I want to be able to nurture my planet
|  | Research methods of employing anthropomorphism within our game | Done | Sprint 7
|  | Create a non-digital concept for how we could use anthropomorphism in our game, based on the research carried out | Done | Sprint 7
Create a digital concept for Praesul, based on the non-digital piece that you created
2 | As a player I want to be able to unlock new sorting categories and their corresponding items
Determine the sorting categories that will feature in the game (Minimum of two initial categories for MVP)
Determine a reward schedule for unlocking new sorting categories
2 | As a player I want a menu system so that I can navigate the game
Main menu background art
|  | Menu mock up | Done | Sprint 3
|  | Menu flow diagram | Done | Sprint 3
Settings/options button
Implement main menu system in Unity
Implement settings menu system in Unity
2 | As a player I want to be able to fill out my collection journal
Create the concept art for the player journal
Create the final artwork for the player journal
Determine what information will be displayed in the player journal
2 | As a player I want to be able to earn in-game achievements that will be recorded in my journal
Come up with a list of basic achievements for the player to earn, these will be recorded in their journal
Create the artwork for the icons/medals that will be displayed next to the achievements in the players journal
2 | As a player I want to have a summary of my planet in my journal so that I can compare with my friends
Create a 'stats' page in collection log (This will be displayed on the left page of the journal until an object is tapped. It will then be replaced with the object info and a back button)
Pull data from Unity and have it display as figures for player to see in collection log (Includes date started, time played in days, hours, minutes and seconds)
2 | As a player I want my planet to be different to other player's planets
Come up with ways of adding variation between players
2 | As a player I want to be able to save my game progress
Research the different methods of saving/loading the game and use this to decide how the player's data should be saved
Implement the fundamentals of the saving system which will save data across play sessions - these should be able to save the planet name and the date of when the planet was created
Implement the ability to keep track of the current amount of energy that the player has
Implement the ability to keep track of the time when the player last played the game (This will allow us to keep track of time between game sessions)
Implement the ability to keep track of the objects that have been placed on the player's planet
Implement the ability to keep track of the player's journal progress
2 | As a player I want to be able to load my game progress
Implement the fundamentals for the loading system - these should be able to load the planet name and the date of when the planet was created
Implement the ability to load the player's energy count upon starting a new play session
Implement the ability to load session times and use this to calculate time between play sessions
Implement the ability to load the player's planet progress
Implement the ability to load the player's journal progress
Implement the ability to load objects in the player's inventory
2 | As a player I want the game to keep track of the time that has passed between play sessions
2 | As a player I want to see a consistent art style
Universal button style
Art style guide
2 | As a player I want to be able to name my planet and have it visible on the game screen
|  | Implement the ability to take in player input for the purpose of naming their planet | Done | Sprint 3
|  | Implement a system that saves the player's planet name across game sessions | Done | Sprint 3
Create a banner for the player's planet name to sit in
In Unity, create a pop-up that displays the planet name at the beginning of each play session
2 | As a player I want to be able to play the game on different devices regardless of resolution
Implement a system in Unity that deals with UI scaling
2 | As a player I want to be able to playtest the game
Create an MVP (minimum viable product)
Create a feedback form that allows players to report bugs
2 | As a player I want to have an elegant UI system
Research mobile game UI; focus primarily on similar games in the market
3 | As a player I want the game to be animated
Animation frames - trees
3 | As a player I want the game to have audio feedback
SFX - button press, new reward unlocked
OST - Day time
OST - Night time
Implement SFX into Unity
Implement OST into Unity
3 | As a player I want the final product to be clean and polished
Carry out in-house testing on appropriate devices
|  | Iterate the game based on tutor feedback, as well as feedback from our target psychographic |  |  | Should this be priority 2 now? Seasons provide optimum times for players to gather and perform certain activities
3 | As a player I want to be able to change the season and have it affect my deocrations |  |  |  | "As a user I want to be able to tend to my planet in different ways"
|  | Create a mood board for Spring | Done | Sprint 2 | "As a user I want to be able to nurture my planet"
|  | Create a mood board for Summer | Done | Sprint 2
|  | Create a mood board for Autumn | Done | Sprint 2
|  | Create a mood board for Winter | Done | Sprint 2
|  | Create a colour palette for Spring | Done | Sprint 2
|  | Create a colour palette for Summer | Done | Sprint 2
|  | Create a colour palette for Autumn | Done | Sprint 2
|  | Create a colour palette for Winter | Done | Sprint 2
3
3

## Risk Assessment
|  | WK8 | WK9 | WK10 | WK11 | WK12
Risk | Impact Level | Likelihood | Likelihood | Likelihood
Poor productivity | High | Medium | Low | Medium |  |  | High
Software bugs | High | Medium | High | High |  |  | Medium
Use of new technology | High | Medium | Medium | Medium |  |  | Low
Not creating an MVP within a reasonable amount of time | High | Medium | Low | Low
A loss of work | Medium | Medium | Medium | Medium
The game may not be what target audience wants | Medium | Medium | Medium | Medium
Risk of not including the key features | Medium | Medium | Medium | Medium
Feature creeping | Medium | Medium | Medium | Medium
Discovering new requirements | Medium | Medium | High | High
Misestimation of project schedule | Medium | High | High | High
Time away due to unforseen circumstances | Medium | Medium | High | Medium
Lack of communication between group members | Medium | Low | Low | Low
Clash of schedules between group members | Low | High | Low | Low
Misestimation of individual tasks | Medium | High | Medium | Medium
Proposed course of action for each risk can be found in detailed Risk Assessment documentation located in Management folder on Github repo