## Backlog
| User Story | Tasks | Status | Week Completed
0 | Pre-production
|  | Market research | Done | Week 4
|  | Create a consumer profile/psychographic | Done | Week 4
Create a risk assessment for the project
Paper prototype
Project timeline?
1 | As a player I want to be able to sort objects
|  | Create concept art for the layout of the sorting screen |  |  | 1 - Necessary for creation of MVP (High priority; marked as Critical on JIRA)
|  | Implement a system in Unity that allows players to drag an item to a category |  |  | 2 - Needed but not required for the MVP (Mid priority; marked as Major on JIRA)
|  | Implement a system in Unity that allows an object from a list to appear in the middle of the screen ready for sorting |  |  | 3 - "Nice to have" if time allows (Low priority; marked as Minor on JIRA)
Implement a system in Unity that checks whether the object has been sorted correctly or incorrectly
Research casual mechanic of sorting/matching
Come up with the two initial sorting categories
Come up with a list of objects (5 for MVP) that can be sorted for each category
|  | Create an animation that will show players how to drag objects to sort them into categories | Done
1 | As a player I want to be able to earn rewards
Research reward schedules
Design a schedule for the rewards that the players can receive
Design the rewards that a player will be able to obtain (seeds)
1 | As a player I want to be able to decorate my planet
Research how to create 'awe' and 'wonder'
Design flowers/trees/bushes that correspond with the seeds the player can unlock
1 | As a player I want to be able to grow different plants
Implement a system in Unity that allows plants to grow in real time
Implement a "growth tick" that requires the player to water their plant every 6 hours in order to progress it's growth
1 | As a player I want to be able to zoom into different parts of my planet
Implement a system in Unity that allows player to use a pinching gesture to zoom in to their planet
|  | Create an pinching hand animation that will be used to show players how to zoom in | Done
1 | As a player I want to be able to rotate around my planet
Implement a system in Unity that allows players to drag left or right to rotate their planet
1 | As a player I want to be able to spend and earn "energy"
Implement a system in Unity that subtracts an energy point every time an object is sorted (successful or unsuccessful)
Implement a system in Unity that allows the player to collect "stars" from fully grown objects
Create a rarity table that dictates how much energy/stars can be earned for each type of object
2 | As a player I want to be able to progress to unlock new sorting categories and their corresponding items
2 | As a player I want a menu system so that I can navigate the game
Main menu background art
Settings/options button
Implement menu system in Unity
2 | As a player I want to be able to fill out my collection journal
2 | As a player I want to have a summary of my planet in my journal so that I can compare with my friends
Create a 'stats' page in collection log
Pull data from Unity and have it display as figures for player to see in collection log
2 | As a player I want to see a consistent art style
Universal button style
Art style guide
2 | As a player I want to be able to name my planet and have it visible on the game screen
Implement the ability to take in player input for the purpose of naming their planet
Implement a system that saves the player's planet name across game sessions
2 | As a player I want to be able to play the game on different devices regardless of resolution
Implement a system in Unity that deals with UI scaling
2 | As a player I want to be able to playtest the game
Create an MVP (minimum viable product)
Create a feedback form that allows players to report bugs
2 | As a player I want to have an elegant UI system
Research mobile game UI; focus primarily on similar games in the market
3 | As a player I want the game to be animated
Animation frames - trees
3 | As a player I want the game to have audio feedback
SFX - button press, new reward unlocked
OST - Day time
OST - Night time
Implement SFX into Unity
Implement OST into Unity
3 | As a player I want the final product to be clean and polished
3 | As a player I want to be able to change the season and have it affect my deocrations
|  | Create a mood board for Spring | Done | Sprint 2
|  | Create a mood board for Summer | Done | Sprint 2
|  | Create a mood board for Autumn | Done | Sprint 2
|  | Create a mood board for Winter | Done | Sprint 2
|  | Create a colour palette for Spring | Done | Sprint 2
|  | Create a colour palette for Summer | Done | Sprint 2
|  | Create a colour palette for Autumn | Done | Sprint 2
|  | Create a colour palette for Winter | Done | Sprint 2
3
3

## Risk Assessment
Risk | Impact Level | Likelihood
Poor productivity | High | Medium |  | High
Software bugs | High | Medium |  | Medium
Use of new technology | High | Medium |  | Low
Not creating an MVP within a reasonable amount of time | High | Medium
A loss of work | Medium | Medium
The game may not be what target audience wants | Medium | Medium | Proposed course of action for each risk can be found in detailed Risk Assessment documentation located in Management folder on Github repo
Risk of not including the key features | Medium | Medium
Feature creeping | Medium | Medium
Discovering new requirements | Medium | Medium
Misestimation of project schedule | Medium | Medium
Time away due to unforseen circumstances | Medium | Medium
Lack of communication between group members | Medium | Low
Clash of schedules between group members | Low | High
Misestimation of individual tasks | Medium | High